## Archie R-V
Archie R-V School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate parents, patrons regarding severe storm safety | 2010 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Educate Board of Education, district staff, parents, patrons and students about the necessity ofsevere weather planning at school and at home.
Educate Parents and patrons regarding severe storm safety. | 2010 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Floods
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Severe Thunderstorms
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Severe Winter Weather
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Extreme Temperatures (Heat and Cold)
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District

## Blue Springs
BLUE SPRINGS SCHOOL DISTRICT (Continuing Participant) (NOT YET PARTICIPATING)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Improve student safety from natural and man-made hazards
Improve Tornado Preparedness with the construction of 5 new High Wind Shelters. When completed 20 out of 22 school buildings will have High Wind Shelters. | 2025 | Ongoing |  | Structure and Infrastructure Projects | High | 1 yrs | Protect students and patrons in case of tornadic weather. | Board of Education | $5.5M | Local 100%
Continue to make two of our High Wind Shelter available to the community (.2 mile radius). 670 Letters mailed annually with info related to the usage. | 2025 | Ongoing |  | Local Plans and Regulations | High | Ongoing | Protect students and patrons in case of tornadic weather. | Board of Education | Low | District
Floods
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Severe Thunderstorms
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Severe Winter Weather
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Extreme Temperatures (Heat and Cold)
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District

## Excelsior Springs
Excelsior Springs School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Improve student safety from natural and man-made hazards.
Construct safe rooms in elementary and high school buildings | 2025 | New | HMPG application submitted | Structure and Infrastructure Projects | High | 2 years | Costs of constructing storm shelters would be high but the benefits outweigh the cost when increased student and community safety is considered. | Excelsior Springs School District | High | Local district as match for federal grant from FEMA or other federal agency
Establish, maintain and communicate an effective crisis management plan. | 2020 | Ongoing | Adopted plan November 2019 | Local Plans and Regulations | High | Ongoing | High payback, low cost | Excelsior Springs School District | Low | District funds
Community partnership to utilize safe rooms.
Communicate with patrons | 2025 | Ongoing |  | Education and Awareness Programs | Medium |  | uncertain | Excelsior Springs School District | Low | District funds
Improve student safety from natural and man-made hazards. | 2025 | Ongoing |  | Education and Awareness Programs | Medium |  | uncertain | Excelsior Springs School District | Low | District funds
Community partnership to utilize safe rooms.
Communicate with patrons | 2025 | Ongoing |  | Education and Awareness Programs | Medium |  | uncertain | Excelsior Springs School District | Low | District funds
Community partnership to utilize safe rooms. | 2025 | Ongoing |  | Education and Awareness Programs | Medium |  | uncertain | Excelsior Springs School District | Low | District funds
Improve student safety from natural and man-made hazards.
Construct safe rooms in elementary and high school buildings | 2020 | New | HMPG application submitted | Structure and Infrastructure Projects | High | 2 years | Costs of constructing storm shelters would be high but the benefits outweigh the cost when increased student and community safety is considered. | Excelsior Springs School District | Estimate of Cost ($) | Funding Source
Establish, maintain and communicate an effective crisis management plan. | 2020 | Ongoing | Adopted plan November 2019 | Local Plans and Regulations | High | Ongoing | High payback, low cost | Excelsior Springs School District | Low | District funds
Severe Thunderstorms
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing | new for 2025 plan | Local Plans and Regulations | High | Ongoing | High payback, low cost | Excelsior Springs School District | Low | District funds
Severe Winter Weather
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing | new for 2025 plan | Local Plans and Regulations | High | Ongoing | High payback, low cost | Excelsior Springs School District | Low | District funds
Extreme Temperatures (Heat and Cold)
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing | new for 2025 plan | Local Plans and Regulations | High | Ongoing | High payback, low cost | Excelsior Springs School District | Low | District funds
Floods
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Excelsior Springs School District | Low | District funds

## Ft. Osage
Fort Osage R-1 School District Mitigation Strategy (Continuing Plan Participant) NOT YET PARTICIPATING
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Continuity of Services
Develop and institute a disaster recovery plan for continuity of student and business services | 2015 | Ongoing |  | Structure and Infrastructure Projects | High | Ongoing | Expect benefit by saving lives and enable district to maintain operations | District Administration | 500000 | Operational funds or bond sale
Increase the capacity for communicating the potential of tornadic activity in a timelier manner. | 2015 | Ongoing |  | Local Plans and Regulations | High | Ongoing | Save lives | District Administration | 0 | N/A
The district will insure staff and students conduct tornado drills during the school year. | 2020 | Ongoing |  |  |  |  | Knowledge should result in lives saved | District and building level teams | Low | Existing
Protect students and staff during severe weather with safe rooms or storm shelter spaces.
Analyze space in existing school buildings and determine if retrofit of existing structures are possible or to design new space in existing or future new schools. Construct safe rooms or shelters as appropriate. | 2020 | New |  | Structure and Infrastructure Projects | High |  | Will result in lives saved | District Administration | Low | FEMA grant and school district funding
Severe Thunderstorms
Continuity of Services
Continuity of services | 2015 | Ongoing |  | Local Plans and Regulations | High | Ongoing | Expect benefit by saving lives and enable district to maintain operations | District and building level teams | 500000 | Sale of bonds or use of designated operating funds
The district will insures staff and students conduct server wearher drills during the school year.
Increase capacity for communication | 2015 | Ongoing |  | Structure and Infrastructure Projects | High | Ongoing | Knowledge should result in lives saved | District and building level teams | 200000 | Sale of bonds or use of designated operating funds
Severe Winter Weather
Continuity of Services
Develop and institute a disaster recovery plan for continuity of student and business services | 2015 | Ongoing |  | Structure and Infrastructure Projects | High | Ongoing | Knowledge should result in lives saved | District and building level teams | 500000 | Operational funds or bond sale
Increase the capacity for communicating the potential of severe winter weather in a timelier manner. | 2015 | Ongoing |  | Local Plans and Regulations | High | Ongoing | Knowledge should result in lives saved | District and building level teams | 0 | N/A
The district will develop strategies for insuring the safety of staff and students during severe winter weather | 2020 | Ongoing |  | Local Plans and Regulations | High | Ongoing | Knowledge should result in lives saved | District and building level teams | Low | Existing

## Grain Valley
Grain Valley School District 2025 Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Increase the safety of students, employees and visitors at the high school with additional shelter space.
Prepare an application for FEMA Mitigation or Pre-Disaster Mitigation grant funds to construct a shelter at the high school. | 2020 | Ongoing | The high school has limited shelter space during severe weather. | Structure and Infratructure Projects | High | 2024 | Lives saved | Grain Valley School District | High | FEMA and school district matching resources
Severe Thunderstorms
Increase shelter capacity at the high school location that would be open to the community during severe weather/tornado.
Prepare an application for FEMA Mitigation or Pre-Disaster Mitigation grant funds to construct a shelter at the high school. | 2020 | Ongoing | The high school has limited shelter space during severe weather. | Structure and Infratructure Projects | High | 2024 | Lives saved | Grain Valley School District | High | FEMA and school district matching resources
Tornadoes
Grain Valley Schools would like to construct in the future a high wind shelter utilizing the standards. outlined in the ICC600.
Prepare an application for FEMA Mitigation or Pre-Disaster Mitigation grant funds to construct a shelter at the high school. | 2025 | New | The high school has limited shelter space during severe weather. | Structure and Infratructure Projects | High |  |  | Grain Valley SD | High | FEMA pre-disaster mitigation grant
Floods
Protect properties from flood events
Work with city and county officials to identify floodprone properties and flash flooding threats | 2025 | New |  | Planning | Low |  |  | Grain Valley SD | :Low | Seek asssistance from city and county officials
Severe Thunderstorms
Grain Valley Schools would like to construct in the future a high wind shelter utilizing the standards. outlined in the ICC600.
Prepare an application for FEMA Mitigation or Pre-Disaster Mitigation grant funds to construct a shelter at the high school. | 2025 | New |  | Structure and Infratructure Projects | High |  |  | Grain Valley SD | High | FEMA pre-disaster mitigation grant
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  |  | Grain Valley SD | Low | District Funds
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | Grain Valley SD | Low | District Funds

## Harrisonville
Harrisonville School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Severe Thunderstorms
Educate district staff, parents and students about the necessity of severe weather planning at school and at home.
Obtain and distribute educational brochures to help staff, students and families become more aware of the dangers of severe thunderstorms and ways they can protect themselves. | 2010 | Ongoing |  | Education and Awareness Programs | Medium | Ongoing | Low cost approach to increase awareness of actions people can take to prevent injury, death and property damage from severe thunderstorms. | Emergency Preparedness Training and Communications | Very low cost | District Budget
Initiate ongoing training and awareness of district staff and students. | 2010 | Ongoing |  | Education and Awareness Programs | Medium | Ongoing | Low cost approach to increase awareness of actions people can take to prevent injury, death and property damage from severe thunderstorms. | Emergency Preparedness Training and Communications | Very low cost | District Budget
Tornadoes
Educate district staff, parents and students about the necessity of severe weather planning at school and at home.
Obtain and distribute educational brochures to help staff, students and families become more aware of the dangers of severe thunderstorms and ways they can protect themselves. | 2010 | Ongoing |  | Education and Awareness Programs | Medium | Ongoing | Low cost approach to increase awareness of actions people can take to prevent injury, death and property damage from tornadoes. | Emergency Preparedness Training and Communications | Very low cost | District Budget
Initiate ongoing training and awareness of district staff and students. | 2010 | Ongoing |  | Education and Awareness Programs | Medium | Ongoing | Low cost approach to increase awareness of actions people can take to prevent injury, death and property damage from tornadoes. | Emergency Preparedness Training and Communications | Very low cost | District Budget
Continue to train students and staff for various disaster situations.
Develop protocols for visitors to district buildings. | 2015 | Ongoing | Tornado procedures updated; lockdown procedures | Local Plans and Regulations | High | Ongoing | This action will provided us with consistent practices for the arrival and departure of district visitors during school hours/business hours. | District and Building Administration | 0 | N/A
Design and build secure entries to district buildings. | 2015 | Ongoing | Two buildings have secure entrance vestibules; assess/update video surveillance annually | Structure and Infrastructure Projects | High | Ongoing | This action will provided us with building entrances that allow for safe arrival and departure of visitors, and it will assist with the maintainence of secure facilities. | District and Building Administration | 50,000- 100,000 | Local District Funds
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  |  | Harrisonville SD | Low | District Budget
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | Harrisonville SD | Low | district
Floods
Educate employees, students and families about steps to protect themselves during heavy rain or flooding events. | 2025 | New |  | Education and Awareness | Low |  |  | Harrisonville SD | Low | district

## Independence
Independence School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Improve student safety from natrual and man-made hazards.
Construct a storm shelter | 2015 | Ongoing | Due to costs and budgetary constraints, we have not constructed any new storm shelters through our district that are available for use. | Structure and Infrastructure Projects | High | Ongoing | Add to new facilities as we can | ISD 30 Board of Education | High | District/Levy/Bond
Implement use of interoperable radio on City emergency system | 2015 | Completed | We have replaced all building level radios in the district to enhance communication with our director of public safety. He has direct communication with the City of Independence Emergency Management Staff. | Structure and Infrastructure Projects | High | 2 years | Implement district wide | ISD 30 Board of Education | 50000 | District Capital
Tornadoes
Construct a tornado shelter
Identify the need for shelter space in one or more school facilities and plan for a shelter space. | 2025 | New |  | Structure and Infrastructure Projects | High |  |  | ISD 30 Board of Education |  | FEMA grant
Floods
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | ISD 30 Board of Education | Low | District
Severe Thunderstorms
Increase awareness of severe weather for those using outdoor school district facilities | 2025 | New |  | Education and Awareness | High |  |  | ISD 30 Board of Education | Low | FEMA grant
Install an alert system for outdoor activities. 2025 New Structure/ Infrastructure High ISD 30 Board Medium | [9 empty] | FEMA grant
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  |  | Independence SD Board | Low | District Funds
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | ISD 30 Board of Education | Low | District

## Kansas City
Kansas City School District #33 Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Safety procedures have been updated for SY15 to increase safety using new recommendations. Increase Safety Drill particpation and evaluate for effectiveness.
Review and implement safety drills and evaluate them for effectiveness | 2015 | Ongoing |  | Education and Awareness Programs | High | Safety drills are placed on a monthly calendar for execution. Reported drills are reviewed regularly with Principals and School Leadership | The only cost is the salaried manpower to evaluate the execution of the drill. The benefit is unmeasurable for the protection of life | KCPS Safety and Security in conjuction with Risk Management | Low | Funding is maintained as an operational budgeted item
Severe Winter Weather
Refine procedures to respond to severe winter weather to ensure the continuation of regular activities while providing a safe and comfortable environment.
Snow removal, surface treatment, vehicle and equipment maintenance, facility maintaince to ensure safe environments | 2015 | Ongoing |  | Unspecified | High | Annually | Cost benefit result is in the reduction of liability claims against the District and increase the safety of all | KCPS Operations Department | 5271000 | Operating budget
Floods
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | KCPS | Low | Operating budget
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | KCPS | Low | operating budget
Severe Thunderstorms
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Severe Winter Weather
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Extreme Temperatures (Heat and Cold)
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District

## Lawson
Lawson School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Improved Safety for students, staff, and community from Tornado hazard.
Construction of FEMA 361 Compliant Safe Room for the High School/Middle School Campus | 2015 | Ongoing | Construction is currently in progress. Expected Completion is June 2020. Funded entirely with local funds. | Structure and Infrastructure Projects | High | 30-Jun-20 | Lives saved | District Board and Administration | $3.8 Million | Local only
Construction of FEMA 361 Safe Room for the Southwest Elementary School Campus | 2015 | Ongoing | Currently in Grant Application stage; Grant completed and submitted to SEMA on February 3, 2020. Expected application approval in 3rd quarter of 2020. | Structure and Infrastructure Projects | High | Jan-22 | Lives saved | District Board and Administration | $3.1 Million | Local plus HMGP Grant
Floods
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | District Board and Administration | Low | District Funds
Severe Thunderstorms
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | District Board and Administration | Low | District Funds
Severe Winter Weather
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | District Board and Administration | Low | District Funds
Extreme Temperatures (Heat and Cold)
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | District Board and Administration | Low | District Funds

## Lee's Summit
Lee's Summit School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Evaluation and Enhancement of Sheltering Areas.
Enhancement/Redefinement of Sheltering areas. Add shelters in new buildings as appropriate. | 2015 | Ongoing | The district continues to monitor its existing shelter areas to determine needs for changes in existing sheltering space | Structure and Infrastructure Projects | Low | Unknown | The cost of such a structural modification or add on will most greatly outweight the estimated use. Such a project would need to be a needed functional space that can be used as a sheltering area. | Safety/Facility Services | High | FEMA grants and school district funds
Evaluate current sheltering needs | 2015 | Ongoing | The district continues to monitor its existing shelter areas to determine needs for additional space | Local Plans and Regulations | Medium | Within the next 5 years. | Evaluation of current sheltering needs to determine if our areas can adequately shelter our school populations should be done every couple of years. There is no cost associated and it is always benefitial to review asset capabilities. | Facility Services | Low | District
Evaluation and Enhancement of Sheltering Areas.
Enhancement/Redefinement of Sheltering areas. Add shelters in new buildings as appropriate. | 2025 | Ongoing, updated | The district continues to monitor its existing shelter areas to determine needs for changes in existing sheltering space | Structure and Infrastructure Projects | Low | Ongoing | The cost of such a structural modification or add on will most greatly outweight the estimated use. Such a project would need to be a needed functional space that can be used as a sheltering area. | Facility Services | High | District Funds
Evaluate current sheltering needs | 2025 | Ongoing, updated | The district continues to monitor its existing shelter areas to determine needs for additional space | Local Plans and Regulations | Medium | Ongoing | Evaluation of current sheltering needs to determine if our areas can adequately shelter our school populations should be done every couple of years. There is no cost associated and it is always benefitial to review asset capabilities. | Facility Services | Low | District Funds
Floods
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Facility Services | Low | District
Severe Thunderstorms
Increase awareness of severe weather for those using outdoor school district facilities | 2025 | New |  | Education and Awareness | High |  |  | Facility Services | Low | District
Install an alert system for outdoor activities. 2025 New Structure/ Infrastructure High District Medium | [9 empty] | District
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  |  | District Board | Low | District Funds
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | District Board | Low | District Funds

## MCC
Metropolitan Community College Mitigation Strategy (Continuing Plan Participant)
MCC Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Severe Winter Weather, Extreme Temperatures, Floods, Severe Thunderstorms, Tornadoes, Human Threats, Evacuations, and Security Plans
Protect human lives, property and mitigate injuries.
Ensure communication channels are working properly between Police Department and other college departments, such as Facilities and Information Technology, to implement equipment or perform maintenance to reduce damage to property and protect lives. | 2025 | Ongoing |  | Structure and Infrastructure Projects | High | 3-5 years | Working with Facilities to maintain landscaping and install lightning protection on campus and college thoroughfares. The cost associated with the landscaping and lightning protection improvements is estimated at $150,000, but these mitigation efforts will ensure a reduction in repair costs over time, and are a valuable life safety enhancement—a benefit that is not easily quantified. Implementing/Updating surveillance equipment across the district is ongoing. The cost of all equipment, landscaping, and lightning protection updates is approximately $900,000 total and the benefit is a reduction in human injuries and property damage, as well as an increase in communications between campus departments. | MCC District Board | 900000 | Funding is through one time funding request (year -end) MCC monies.
Ensure MCC emergency response procedures are reviewed and employees trained annually. | 2025 | Ongoing |  | Education and Awareness Programs | Medium | 1-2 years | MCC has existing procedures in place to consistently reeducate students and employees. Safety awareness remains a top priority. The time and resource cost is built into operational overhead; the benefit is promoting safety and injury mitigation through emergency preparedness and readiness. | MCC District Board | 0 | Funding is maintained as an operational budgeted item in MCC budget.
Development of an updated emergency operational plan addressing both natural and human threats | 2025 | Ongoing |  | Law enforcement | High | 1 year | The time and resource cost incident to MCC-PD updating and refining its Emergency Operational Plan is built into operational overhead; the benefit is to prevent and reduce human injury and protect lives. | MCC District Board | 0 | Funding is maintained as an operational budgeted item in MCC budget

## NKC
North Kansas City School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
To ensure the best possible severe weather sheltering possible.
Reassess sheltering locations and if appropriate add safe rooms or shelters to existing buildings or as new buildings are planned and built | 2015 | Ongoing |  | Structure and Infrastructure Projects | Medium | Ongoing | Reduce potential for loss of life | Safety & Security | Low | District
Floods
To improve our evacuation reponse and reduce potential damage due to flooding.
Improve response to possible flooding from levee failure at NKCHS | 2015 | Ongoing |  | Structure and Infrastructure Projects | Low | Ongoing | Reduce potential for loss of life | NKCPD, Safety & Security | Low | District
Severe Thunderstorms
Increase awareness of severe weather for those using outdoor school district facilities | 2025 | New |  | Education and Awareness | High |  |  | NKC Board of Education | Low | FEMA grant
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  |  | NKC Board of Education | Low | District Funds
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | NKC Board of Education | Low | District Funds

## Oak Grove R-VI
Oak Grove R-VI School District Mitigation Strategy (Continuing Plan Participant) NOT YET PARTICIPATING
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Construct a district storm shelter, revise severe weather policies, conduct additional drills.
Construct a district storm shelter, revise severe weather policies, conduct additional drills | 2015 | Ongoing |  | Structure and Infrastructure Projects | High | 3 years | Revise policies and procedures and conducting additional drills would require no additional cost. $2 to 3 million dollars was estimated as a storm shelter cost. While the cost is significant, the benefits far outweigh the cost. | Oak Grove R-VI School District Superintendent and Board of Education | High | District capital projects funds and FEMA/SEMA grant funding
Review and revise and effective crisis management plan | 2015 | Ongoing |  | Local Plans and Regulations | High | 3 years | Employing outside services for assistance is costly. The revisiting of existing crisis management committee and existing plan will result in a program that will adequately serve the needs of the district utilizing existing resources. | School District Administration and SRO | Low | District funds
Floods
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Oak Grove Board of Education | Low | District funds
Severe Thunderstorms
Increase awareness of severe weather for those using outdoor school district facilities | 2025 | New |  | Education and Awareness | High |  |  | Oak Grove Board of Education | Low | District funds
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  |  | Oak Grove Board of Education | Low | District funds
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | Oak Grove Board of Education | Low | District funds

## Park Hill
Park Hill School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Increase safety of students, staff and visitors from severe weather by adding shelter space.
Seek Mitigation grant to add storm shelters to existing sport stadiums | 2025 | New |  | Structure and Infrastructure Projects | Medium | 2025 to apply; ongoing to completion | High - lived saved | Park Hill Board of Education/District | High | FEMA grant and local match
Ensure a safe, caring environment for students, staff and visitors.
Purchase a portable, three-phase generator to supply electrical power in case of an emergency. | 2010 | Ongoing | Maintain three-phase generator | Structure and Infrastructure Projects | High | Ongoing | Would ensure electricial power continuity for a variety of threats/hazards. | Park Hill Board of Education/District | Low | District
Severe Winter Weather
Ensure a safe, caring environment for students, staff and visitors.
We purchased three generators in the event of power outages. | 2020 | Completed | Maintain three-phase generator | Structure and Infrastructure Projects | High | Ongoing | Would ensure electricial power continuity for a variety of threats/hazards. | Park Hill Board of Education/District | Low | District
Floods
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Park Hill Board of Education/District | Low | District
Severe Thunderstorms
Increase awareness of severe weather for those using outdoor school district facilities | 2025 | New |  | Education and Awareness | High |  | Cost is negligible, benefit is saving of life | Park Hill Board of Education/District | Low | District
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  | Cost is negligible, benefit is saving of life | Park Hill Board of Education/District | Low | District Funds
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  | Cost is negligible, benefit is saving of life | Park Hill Board of Education/District | Low | District Funds

## Park University
Park University Mitigation Strategy (Continuing Plan Participant) NOT YET PARTICIPATING
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Perform a campus-wide Tornado Drill in April of each year.
Coordinate campus-wide tornado drill in the month of April each year after Goal 1 is complete. Optional: Coordinate with City of Parkville to hold drill on same date as city-wide tornado drill. | 2015 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Campus-wide emergency response preparation - drill will identify strengths and weaknesses of planned procedures and allow for any weaknesses to be addressed. | EHS Compliance Coordinator | Low | N/A
Post Emergency Evacuation Routes in all buildings and update as needed.
Coordinate with local NWS personnel to ensure chosen Storm Shelter locations are acceptable. | 2015 | Ongoing |  | Local Plans and Regulations | High | Ongoing | Providing the best shelter locations possible in each campus building to ensure the best protection available in the event of a tornado or severe weather emergency. | EHS Compliance Coordinator | Low | Campus Safety Payroll Budget
Print, laminate, and post evacuation maps at strategic locations in all buildings. | 2015 | Ongoing |  | Local Plans and Regulations | High | Ongoing | Providing /making available emergency evacuation/shelter information to the campus community. | EHS Compliance Coordinator | Low | Campus Safety Payroll Budget and EHS Budget
Review current emergency evacuation routes and maps for accuracy and feasibility. | 2015 | Ongoing |  | Local Plans and Regulations | High | Ongoing | Ensuring that all spaces within a building are accounted for and accurately planning evacuation routes. Losses avoided include submitting inaccurate information to campus community, thus causing confusion during an actual emergency. | EHS Compliance Coordinator | Low | Campus Safety Payroll Budget
Floods and Severe Thunderstorms
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Low | Park Univ Board | Low | Park U
Severe Winter Weather
Help employees and students be prepared for and protect themselves during severe weather events
Educate employees and students about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  | Low | Park Univ Board | Low | Park U
Extreme Temperatures (Heat and Cold)
Educate employees and students about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  | Low | Park Univ Board | Low | Park U

## Platte County R-3
Platte County R-3 School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes and Severe Thunderstorms
Improved Safety for students, staff and community from hazard of tornado.
Conduct emergency drills throughout district (severe weather, fire, intruder, earthquakes) | 2010 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Avoid injury, loss of life. | Platte County R-3 School District Administration | Low | School District Budget
Consider sheltering options for students, staff and visitors during tornadoes and other natural hazards.
Investigate the cost of adding storm shelters to our existing facilities. | 2015 | Ongoing |  | Structure and Infrastructure Projects | High | Ongoing | Cost of shelters would be significant however this approach is the best way of keeping people safe during a tornado. Many lives would be saved. | Platte County R-3 School District Administration | High | TBD
Severe Winter Weather
Improve communications to all stakeholders for severe winter weather situation.
Develop a comprehensive communication plan when severe winter weather causes the district to close. | 2015 | Completed | Revised District and School Crisis Plans | Local Plans and Regulations | High | 2019-2020 school year | Avoid injury, loss of life. | Platte County R-3 School District Administration | Low | School District Budget
Continue to work with maintenance and custodial crews to proactively walk buildings to ensure the school are ready for school during winter events.
| 2025 | ongoing | Revised District and School Crisis Plans | Local Plans and Regulations | High | ongoing | Avoid injury, loss of life. | Platte County R-3 School District Administration | Low | School District Budget
Tornadoes
Work with architects to determine the best location for students and staff when taking shelter in our building for severe weather and tornadoes
Evaluate safe room or shelter space for each building | 2025 | ongoing |  |  | Medium | ongoing | Avoid injury, loss of life. | Platte County R-3 School District Administration | Medium | School District Budget
Extreme Temperatures
Work with our Energy management company to install energy system controls and find ways to reduce energy use during extreme heat waves.
| 2025 | ongoing |  | Structure and Infrastructure Projects | Medium | Ongoing | Avoid injury, loss of life. | Platte County R-3 School District Administration | Medium | FEMA Grants

## Pleasant Hill R-III
Pleasant Hill R-III School District Mitigation Strategy (Continuing Plan Participant) NOT YET PARTICIPATING
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes and Severe Thunderstorms
Disseminate information to patrons based upon survey information
Meet with school personnel regarding school district safety and emergency preparedness | 2010 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is minimal but information will be invaluable for strudants, staff and patrons. | School Board | Low | District
Initiate ongoing information dissemination and awareness for the district’s staff, parents and patrons during faculty and staff in-service | 2010 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is minimal but information will be invaluable for strudants, staff and patrons. | School Board | Low | District
Educate Board of Education, district staff, parents, patrons and students about the necessity of severe weather planning at school and at home.
Create an electronic survey to be sent home annually to parents and present safety information to parents, staff and Board of Education. | 2010 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is minimal but information will be invaluable for strudants, staff and patrons. | School Board | Low | District
Upgrade storm sheltering capacities and facilities in the district.
Construct tornado safe rooms in district facilities. | 2015 | Ongoing |  | Structure and Infrastructure Projects | High | 3 to 5 years | $4 million cost. Benefit would to better shelter our students, staff and patrons in the event of severe weather. | School Board | High | FEMA Grant/Local Funds
Provide storm shelters for every student in every building in the district
Review building spaces to identify where improvements are needed to improve student safety | 2025 | New |  | Planning | High |  |  | School Board | Low | District funds
Provide tornado shelter for every building in the district
Seek funds where needed to increase shelter capacity in district buildings | 2025 | New |  | Structure and Infrastructure Projects | High |  |  | School Board | High | FEMA grant funds
Floods
Improve storm water issues through out the district
| 2025 | New | Enlist assistance from county stormwater program for guidance | Structure and Infrastructure Projects | Medium |  |  | School Board | High | FEMA grant funds
Severe Winter Weather
Improve HVAC units to maintain building temps and student air quality
| 2025 | New |  | Structure and Infrastructure Projects | High |  |  | School Board | Medium | District funds
Improve HVAC units to maintain heat and air quality in the buildings
| 2025 | New |  | Structure and Infrastructure Projects | High |  |  | School Board | Medium | District funds
Extreme Temperature
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | School Board | Low | District funds

## Raymore-Peculiar
Raymore-Peculiar School District Mitigation Strategy (Continuing Plan Participant)
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Increase public awareness and understanding the benefits of "safe rooms."
Develop, distribute informational materials on safe rooms. | 2015 | Ongoing |  | Education and Awareness Programs | Medium | Ongoing | Low cost mechanism to increase student safety. | Ray-Pec District Administration | Low | District
Increase public awareness and understanding the benefits of tornado shelters
Providing materials to patrons that we do have shelters in place to withstand the high winds of a tornado | 2025 | Ongoing |  | Education and Awareness Programs | Medium | Ongoing |  | Ray-Pec District Administration | Low | District
Severe Thunderstorms
Maintain current weather alert systems in all district facilities.
Test, monitor, and repair all weather alert systems annually. | 2015 | Ongoing |  | Structure and Infrastructure Projects | High | Ongoing | Will ensure proper function of alerting systems. | Ray-Pec District Administration | Low | District
Maintain current weather alert systems in all district facilities
Test, monitor, and repair all weather alert systems annually.As needed, replace equipment or add new systems to ensure that all employees and staff at all schools are informed if they should take action to shelter due to hazardous conditions. | 2025 | Ongoing |  | Unspecified | Unspecified
Extreme Temperature
Ensure no injuries due to exposure to heat.
Prove water and cooling stations for bus drivers. | 2025 | Ongoing |  | Local Plans and Regulations | High | 10/1/2024 |  | Ray-Pec District Admin | Medium | District
Provide water stations for students and employees in all buildings | 2025 | Ongoing |  | Local Plans and Regulations | High |  |  | Ray-Pec District Admin | Medium | District
Floods
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Facility Services | Low | District
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  |  | Ray-Pec District Board | Low | District

## Richmond SD
Richmond, MO School District Mitigation Goals and Actions (New Participant) NOT YET PARTICIPATING
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate parents, patrons regarding severe storm safety | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Educate Board of Education, district staff, parents, patrons and students about the necessity ofsevere weather planning at school and at home.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Floods
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Severe Thunderstorms
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Severe Winter Weather
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Extreme Temperatures (Heat and Cold)
Disseminate information to Board of Education, district staff, parents, patrons and students regarding the threat of severe weather and preventative measures that can be taken to mitigate the hazards associated with severe weather.
Educate Parents and patrons regarding severe storm safety. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District

## Sherwood Cass
SHERWOOD-CASS SCHOOL DISTRICT | NOT YET PARTICIPATING
2025 MITIGATION GOALS AND ACTIONS | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes and Severe Thunderstorms
Disseminate information to Board of Education, district staff, parents, patrons and studentsregarding the threat of severe weather and preventative measures that can be taken to mitigate the hazardsassociated with severe weather.
Educate parents, patrons regarding severe storm safety | 2023 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Improve Tornado Preparedness with the construction of storm shelters | 2023 | New | Have identified a location on the school property for a shelter | Structure and Infrastructure Projects | High | unknown, dependent upon availability of grant funds | Protect students and patrons in case of tornadic weather. | Board of Education | High; not yet designed; 2023 bond issue to be submitted to voters and if approved, will have 25% to match FEMA funds | FEMApre-hazard grant
Floods
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education | Low | District
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low |  |  | Board of Education | Low | District
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low |  |  | Board of Education | Low | District

## Smithville R-II
Smithville R-II School District 2025 Mitigation Strategy (Continuing Plan Participant) NOT YET PARTICIPATING
Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
To protect the health and safety of students, employees, and community members from natural and man-made hazards
Improve Tornado Prepardeness by Construct a storm shelter/Safe Room. • Implement tornado readiness and response procedures in curriculum. • Conduct additional drills. (Tornado, Intruder, Fire) | 2010 | Ongoing | Constructed a storm shelter at the high school | Structure and Infrastructure Projects | High | Ongoing | Conducting additional drills would not require additional funding, however we feel that two drills per year is sufficient for students in grades 6 through 12, and a minimum of four drills are required for students in grades kindergarten through fifth. | Board of Education, Superintendent | Low | District Funding
Tornadoes
Develop a full AAR method to better incorporate action plans into training and education plan to improve overall response and future exercises.
| 2025 | ongoing |  | Planning & Regulations | Medium | ongoing |  | Board of Education, Superintendent | Medium | District
Floods
Increase awareness and safety from hazards
Establish, maintain and communicate an effective crisis management plan. | 2025 | Ongoing |  | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | Board of Education, Superintendent | Low | District
Severe Thunderstorms
Increase awareness of severe weather for those using outdoor school district facilities | 2025 | New |  | Education and Awareness | High |  |  | Board of Education, Superintendent | Low | District
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New |  | Education and Awareness | Low | ongoing |  | Board of Education, Superintendent | Low | District
Extreme Temperatures (Heat and Cold)
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New |  | Education and Awareness | Low | ongoing |  | Board of Education, Superintendent | Low | District

## West Platte R-II
West Platte R-II School District 2025 Mitigation Strategy (Continuing Plan Participant)
West Platte R-II SD Mitigation Goals and Action Steps | Plan Year | Status of Project | Status Explanation | Type of Mitigation Activity | Priority | Date of Completion | Cost/Benefit Review | Primary Agency Responsible for Implementation/Administration | Estimate of Cost ($) | Funding Source
Tornadoes
Improved Safety for students, staff and community from hazard of tornado.
Consider including the Construction of a "hardened shelter" as part of the upcoming capital improvement project. | 2010 | Completed | Elementary gymnasium was built to FEMA standards and is said to have the ability to withstand a direct hit from a tornado. | Structure and Infrastructure Projects | Medium | 2017-2018 | Avoid injury, loss of life. | West Platte District Board of Education | High | District Capital Projects Budget/FEMA Grant
Establish, maintain and communicate key messages from an effective crisis management plan. | 2025 | New |  | Education and Awareness Programs | Medium |  | reduce risks to injury or loss of life | West Platte District Board of Education | Low | District Board
Severe Thunderstorms
Improved Safety for students, staff and community from hazard of severe thunderstorms.
Consider including the Construction of a "hardened shelter" as part of the upcoming capital improvement project. | 2010 | Completed | Elementary gymnasium was built to FEMA standards and is said to have the ability to withstand a direct hit from a tornado. | Structure and Infrastructure Projects | Medium | 2017-2018 | Avoid injury, loss of life. | West Platte District Board of Education | High | District Capital Projects Budget/FEMA Grant
Establish, maintain and communicate key messages from an effective crisis management plan. | 2025 | New | District maintains a crisis communications plan and will continue to expand and update it | Education and Awareness Programs | Medium |  | reduce risks to injury or loss of life | West Platte District Board of Education | Low | District Board
Floods
Increase awareness and safety from hazards
Establish, maintain and communicate key messages from an effective crisis management plan. | 2025 | Ongoing | District maintains a crisis communications plan and will continue to expand and update it | Education and Awareness Programs | High | Ongoing | Cost is negligible, benefit is saving of life | West Platte District Board of Education | Low | District
Severe Winter Weather
Help employees and families be prepared for and protect themselves during severe weather events
Educate employees, students and families about steps to protect themselves during severe winter weather | 2025 | New | District maintains a crisis communications plan and will continue to expand and update it | Education and Awareness | Low |  |  | West Platte District Board of Education | Low | District
Extreme Temperatures (Heat and Cold)
Increase awareness and safety from hazards
Educate employees, students and families about steps to protect themselves during severe winter weather or extreme heat | 2025 | New | District maintains a crisis communications plan and will continue to expand and update it | Education and Awareness | Low |  |  | West Platte District Board of Education | Low | District